## Overview
MediaWave Streaming — Final Project Timeline
ISM 6562 · Big Data for Business Applications · Project #10
Key Dates |  | Team Roles
Day 1 (Kickoff) | Friday, April 24, 2026 | Juan | Integration Lead + Stage 1 (HDFS) | Has 16 GB machine. Docker + networking + HDFS.
First integration checkpoint | Sunday, April 26, 2026 | Yusuke | Stage 2 (Spark batch) | Python/data fluency. Joins, aggregations, PySpark.
Technical freeze target | Friday, May 1, 2026 | Quang | Stage 3 (Kafka + Streaming) | Distributed systems curiosity. Producer + consumer.
Final report + slides PDF | Monday, May 4, 2026 | Alex | Stage 4 (Airflow) + Data Quality | Clean code, modular Python. DAGs, retries, SLAs.
Final dry-run | Tuesday, May 5, 2026 | Helen | PM + Writer | Strong English writing. Report, slides, rehearsals.
Submission + In-class presentation | Wednesday, May 6, 2026
Progress Summary
Total tasks | 110 | Ground rules
Tasks marked done | 9 | • Daily 10-min standup at 9 PM
Completion % | 8.182% | • Every person commits to GitHub every day (empty commits OK)
• Every handoff is a 15-min video call, not a text message
• End-of-day status in group chat: green / yellow / red

## Daily Tasks
Day | Date | Person | Stage/Area | Task | Status | Notes
1 | Thu Apr 23 | TEAM | Kickoff | 90-min kickoff call: claim Project #10 on Canvas, confirm roles, set standup time, create shared Drive
1 | Fri Apr 24 | Helen | Repo setup | Build folder structure with .gitkeep files; README skeleton with all section headers
1 | Fri Apr 24 | Juan | Stage 1 | Copy 4 weekly docker-compose files into docker-research/ | Done
1 | Fri Apr 24 | Juan | Stage 1 | Build conflict table: every service, port, volume, network across 4 files (DO NOT write merged file yet) | Done
1 | Fri Apr 24 | Yusuke | Stage 2 | Download all 5 MediaWave files + generate_data.py
1 | Fri Apr 24 | Yusuke | Stage 2 | Set up Python venv and install pyspark 3.5.0, pandas, jupyter
1 | Fri Apr 24 | Yusuke | Stage 2 | Read generate_data.py end-to-end carefully (single most valuable hour)
1 | Fri Apr 24 | Yusuke | Stage 2 | Add Stage 2 section to docs/design.md: columns, types, nullable fields, join keys per dataset
1 | Fri Apr 24 | Yusuke | Stage 2 | Smoke test: load user-profiles.csv.gz with Spark, print schema, show 5 rows
1 | Fri Apr 24 | Quang | Stage 3 | Re-read Week 10 Kafka materials; pip install kafka-python
1 | Fri Apr 24 | Quang | Stage 3 | Add Stage 3 section to docs/design.md: topic name, partitions, key design, retention, producer strategy
1 | Fri Apr 24 | Quang | Stage 3 | Write producers/event_producer.py skeleton that prints fake JSON events to stdout (no Kafka yet)
1 | Fri Apr 24 | Alex | Stage 4 | Re-read Week 11 Airflow materials
1 | Fri Apr 24 | Alex | Stage 4 | Add Stage 4 section to docs/design.md: DAG sketch, task list, dependencies, quality gate locations
1 | Fri Apr 24 | Alex | Stage 4 | Create src/common/quality.py with 3 functions: check_row_count, check_nulls, check_unique_key; validate in notebook
2 | Sat Apr 25 | Juan | Stage 1 | Start docker-compose.yml from Week 11 as base; add HDFS services on shared network mediawave-net with mem_limit | Done
2 | Sat Apr 25 | Juan | Stage 1 | Add Spark services (spark-master, spark-worker) from Week 9 | Done
2 | Sat Apr 25 | Juan | Stage 1 | Boot partial stack, verify HDFS UI at :9870 and Spark UI at :8080 | Done
2 | Sat Apr 25 | Juan | Stage 1 | Smoke test: docker exec -it namenode hdfs dfs -mkdir /test && hdfs dfs -ls / | Done
2 | Sat Apr 25 | Yusuke | Stage 2 | Create src/common/schemas.py with explicit StructType for all 5 datasets
2 | Sat Apr 25 | Yusuke | Stage 2 | Build notebooks/02-spark-transforms.ipynb: load each dataset with schema, show count/describe/null counts
2 | Sat Apr 25 | Yusuke | Stage 2 | Draft reusable clean_and_save function (dropDuplicates + dropna + write Parquet)
2 | Sat Apr 25 | Yusuke | Stage 2 | Apply cleaning to 2 simplest datasets (user-profiles, streaming-quality) → local ./curated/
2 | Sat Apr 25 | Quang | Stage 3 | Expand event_producer.py: read viewing-history.csv.gz, sort by timestamp, publish JSON to user-viewing-events
2 | Sat Apr 25 | Quang | Stage 3 | Verify via kafka-console-consumer; ~50 events/sec flowing
2 | Sat Apr 25 | Alex | Stage 4 | Install Airflow locally or via light Docker container
2 | Sat Apr 25 | Alex | Stage 4 | dags/batch_pipeline.py with 5 placeholder BashOperator tasks: ingest, validate, clean, join, aggregate
2 | Sat Apr 25 | Alex | Stage 4 | Config: schedule_interval=@daily, catchup=False, retries=2, retry_delay=5min; verify one successful run
2 | Sat Apr 25 | Helen | Report | First architecture diagram v1 → docs/architecture-diagram.png
2 | Sat Apr 25 | Helen | Report | Draft report sections 1 (Executive Summary) and 2 (Architecture Design)
3 | Sun Apr 26 | Juan | Stage 1 | Add Kafka (zookeeper + kafka) from Week 10 to docker-compose | Done
3 | Sun Apr 26 | Juan | Stage 1 | Add Airflow (postgres + airflow) from Week 11 to docker-compose | Done
3 | Sun Apr 26 | Juan | Stage 1 | Add profiles: ['full'] tags on Kafka + Airflow for lightweight mode
3 | Sun Apr 26 | Juan | Stage 1 | Create HDFS zones: /landing/{5 subfolders}, /curated, /analytics; load all 5 raw files via hdfs dfs -put | Done
3 | Sun Apr 26 | Juan | Stage 1 | NOON HANDOFF: 15-min call with B to walk through reading HDFS from Spark container
3 | Sun Apr 26 | Juan | Stage 1 | Afternoon: draft README setup instructions
3 | Sun Apr 26 | Yusuke | Stage 2 | Update src/common/config.py: LANDING = hdfs://namenode:9000/landing, etc.
3 | Sun Apr 26 | Yusuke | Stage 2 | Move notebook into Spark container environment; run Day 2 code against HDFS paths (should work unchanged)
3 | Sun Apr 26 | Yusuke | Stage 2 | Clean remaining 3 datasets: viewing-history, content-catalog (JSON), user-interactions (JSON)
3 | Sun Apr 26 | Yusuke | Stage 2 | Verify all 5 curated Parquet files readable via spark.read.parquet; commit to src/transforms/
3 | Sun Apr 26 | Quang | Stage 3 | Write src/streaming/consumer.py: Structured Streaming reads user-viewing-events, parses JSON, writes to console
3 | Sun Apr 26 | Quang | Stage 3 | Add windowed aggregation: count of play events per 1-min tumbling window per content_id
3 | Sun Apr 26 | Quang | Stage 3 | Verify end-to-end flow: producer → Kafka → consumer with aggregation
3 | Sun Apr 26 | Alex | Stage 4 | Replace placeholders with SparkSubmitOperator or spark-submit-via-BashOperator
3 | Sun Apr 26 | Alex | Stage 4 | Wire ingest, validate, clean tasks to real logic; allow 1-2h for Airflow↔Spark networking debugging
3 | Sun Apr 26 | Helen | Report | Update architecture diagram to reflect what A actually built
3 | Sun Apr 26 | Helen | Report | Start collecting screenshots: HDFS UI with files, Spark UI with workers, Airflow DAG
4 | Mon Apr 27 | Juan | Infra | Stress test: docker compose down -v && docker compose --profile full up -d; confirm cold-boot works
4 | Mon Apr 27 | Juan | Infra | Write lightweight mode section of README with explicit commands; on-call for B/C/D debugging
4 | Mon Apr 27 | Yusuke | Stage 2 | join_enrich.py: Join 1 viewing-history ⨝ content-catalog on content_id
4 | Mon Apr 27 | Yusuke | Stage 2 | Join 2 viewing-history ⨝ user-profiles on user_id
4 | Mon Apr 27 | Yusuke | Stage 2 | Join 3 viewing-history ⨝ streaming-quality on session key
4 | Mon Apr 27 | Yusuke | Stage 2 | aggregate_business.py Agg 1: top content by genre per week → /analytics/top_content_by_genre/ (partitioned by week)
4 | Mon Apr 27 | Yusuke | Stage 2 | Agg 2: completion rate by subscription tier → /analytics/completion_by_tier/
4 | Mon Apr 27 | Quang | Stage 3 | Write Lambda vs Kappa justification in docs/design.md (Lambda fits MediaWave)
4 | Mon Apr 27 | Quang | Stage 3 | Enrich single streaming consumer: multiple aggregations in same job (top content + unique viewers + avg completion)
4 | Mon Apr 27 | Alex | Stage 4 | Implement real quality gate between clean and join: read curated Parquet, run check_nulls + check_row_count, raise AirflowFailException on fail
4 | Mon Apr 27 | Alex | Stage 4 | Wire join and aggregate tasks to B's scripts; run full DAG end-to-end and screenshot green run
4 | Mon Apr 27 | Helen | Report | Draft Section 3 (Implementation): Kafka topic design, Airflow DAG structure, data quality strategy
4 | Mon Apr 27 | Helen | Slides | Take high-quality screenshots → presentation/screenshots/; create slides.pptx with slides 1-5 (title, agenda, team, problem, architecture)
5 | Tue Apr 28 | Juan | Infra | Pin all image versions in docker-compose (no :latest)
5 | Tue Apr 28 | Juan | Infra | Write detailed README setup instructions; test on fresh clone
5 | Tue Apr 28 | Juan | Infra | Final docs/architecture-diagram.png polish
5 | Tue Apr 28 | Yusuke | Stage 2 | Agg 3: quality impact on completion → /analytics/quality_impact/
5 | Tue Apr 28 | Yusuke | Stage 2 | Agg 4: DAU by week + cohort retention → /analytics/dau_retention/ (partitioned by week)
5 | Tue Apr 28 | Yusuke | Stage 2 | notebooks/04-exploration.ipynb: load each analytics Parquet, produce 4-5 matplotlib plots (one per business question); hand to E
5 | Tue Apr 28 | Yusuke | Stage 2 | Write src/transforms/README.md listing each analytics table, schema, business question answered
5 | Tue Apr 28 | Quang | Stage 3 | Add checkpointing to streaming consumer (required for fault tolerance)
5 | Tue Apr 28 | Quang | Stage 3 | Fault test: kill consumer mid-run, restart, verify resume without duplication
5 | Tue Apr 28 | Quang | Stage 3 | Write src/streaming/README.md: topics, partitioning rationale, windowing choices
5 | Tue Apr 28 | Alex | Stage 4 | Test idempotency: run batch DAG twice, confirm /curated/ and /analytics/ identical (use .mode('overwrite'))
5 | Tue Apr 28 | Alex | Stage 4 | Add sla=timedelta(hours=2) to critical tasks; configure retries with exponential backoff
5 | Tue Apr 28 | Alex | Stage 4 | Set email_on_failure=True, email=... in default_args (satisfies failure alerting in one line)
5 | Tue Apr 28 | Alex | Stage 4 | dags/streaming_monitor.py: runs every 15 min, checks Kafka topic lag and consumer health
5 | Tue Apr 28 | Helen | Report | Draft Section 4 (Business Insights) using B's plots; one paragraph per business question with specific numbers
5 | Tue Apr 28 | Helen | Slides | Slides 6-15: architecture, stage-by-stage walkthrough with screenshots
5 | Tue Apr 28 | Helen | Report | Start Section 5 (Scalability) — gather specific numbers from A (infra), C (Kafka), D (Airflow)
6 | Wed Apr 29 | Juan | Infra | Fresh-machine test: docker compose down -v, follow own README as if grader; time each step, fix unclear parts
6 | Wed Apr 29 | Juan | Infra | Ask Person E to clone and run setup — any issue E hits = README bug
6 | Wed Apr 29 | Yusuke | Stage 2 | Add partitioning to remaining large aggregations (.write.partitionBy('week').parquet(...))
6 | Wed Apr 29 | Yusuke | Stage 2 | Clear docstrings on every Spark script
6 | Wed Apr 29 | Yusuke | Demo | Short screen capture 2-3 min: run a Spark job, show Parquet output, Spark SQL query showing a business finding
6 | Wed Apr 29 | Quang | Demo | Short screen capture 2-3 min: start producer → events in console → Structured Streaming aggregates updating
6 | Wed Apr 29 | Quang | Stage 3 | Final Lambda/Kappa writeup polished
6 | Wed Apr 29 | Alex | Demo | Short screen capture 2-3 min: Airflow UI, trigger batch DAG, tasks going green, quality gate failing on injected bad data, retry behavior
6 | Wed Apr 29 | Helen | Report | Full pass through report sections 1-5; target 7-8 pages
6 | Wed Apr 29 | Helen | Slides | Finalize all slides (20-25 for 10-12 min = ~30 sec/slide)
6 | Wed Apr 29 | Helen | Presentation | Assign presentation sections: each person presents their stage (~2 min each = 10 min + intro + closing)
7 | Thu Apr 30 | TEAM | Review | Cross-review day: code review, report review, slide review; honest feedback
7 | Thu Apr 30 | Juan | Infra | Final docker compose up -d test; tag release v0.9-rc
7 | Thu Apr 30 | Yusuke | Stage 2 | Redo any weak aggregation; improve visualizations
7 | Thu Apr 30 | Quang | Stage 3 | Polish streaming docs
7 | Thu Apr 30 | Alex | Stage 4 | Polish DAG documentation
7 | Thu Apr 30 | Helen | Presentation | Full dry-run of presentation live on video call; time it; cut to ≤12 min
7 | Thu Apr 30 | Helen | Presentation | Prepare 3-4 Q&A answers (schema evolution, Parquet vs Avro, 3AM failure, late-arriving events)
8 | Fri May 1 | TEAM | Integration | Morning 2h team call: everyone watches A run compose up, D trigger DAG, C stream demo; find bugs, fix immediately
8 | Fri May 1 | Juan | Infra | Final docker-compose polish; tag v1.0-submission-candidate; add Known Issues to README if needed
8 | Fri May 1 | Yusuke | Stage 2 | Final Spark script polish; all scripts commented, all outputs documented
8 | Fri May 1 | Quang | Stage 3 | Final streaming docs; Kafka topic justification finalized
8 | Fri May 1 | Alex | Stage 4 | Final DAG polish; airflow dags test passes; monitoring DAG confirmed running
8 | Fri May 1 | Helen | Report | Report final pass
8 | Fri May 1 | Helen | Slides | Slides final pass
8 | Fri May 1 | TEAM | Rehearsal | Second full presentation dry-run
9 | Sat May 2 | TEAM | Review | Each person reviews full report; red-pen feedback to E
10 | Sun May 3 | Helen | Report | Incorporate feedback; third full presentation rehearsal
11 | Mon May 4 | Helen | Submit | Final report PDF exported
11 | Mon May 4 | Helen | Submit | Final slides PDF exported; commit both
12 | Tue May 5 | TEAM | Rehearsal | Final dry-run, ideally on actual presentation room equipment
13 | Wed May 6 | TEAM | Submit | Final commit; confirm prof-tcsmith has repo access; submit
13 | Wed May 6 | TEAM | Presentation | In-class presentation (Week 12 schedule)

## Per-Person Summary
Task Counts by Person
Person | Role | Total Tasks | Done | Progress %
Juan | Integration Lead + Stage 1 (HDFS) | 0 | 0 | 0%
Yusuke | Stage 2 (Spark batch) | 0 | 0 | 0%
Quang | Stage 3 (Kafka + Streaming) | 0 | 0 | 0%
Alex | Stage 4 (Airflow) + Data Quality | 0 | 0 | 0%
Helen | PM + Writer + Presenter | 0 | 0 | 0%
TEAM | Team-wide tasks | 8 | 0 | 0%
TOTAL |  | 8 | 0 | 0%
Task Counts by Day
Day | Date | Total | Done | Progress %
1 | Fri Apr 24 | 15 | 2 | 13.33%
2 | Sat Apr 25 | 15 | 4 | 26.67%
3 | Sun Apr 26 | 17 | 3 | 17.65%
4 | Mon Apr 27 | 13 | 0 | 0%
5 | Tue Apr 28 | 17 | 0 | 0%
6 | Wed Apr 29 | 11 | 0 | 0%
7 | Thu Apr 30 | 7 | 0 | 0%
8 | Fri May 1 | 8 | 0 | 0%
9 | Sat May 2 | 1 | 0 | 0%
10 | Sun May 3 | 1 | 0 | 0%
11 | Mon May 4 | 2 | 0 | 0%
12 | Tue May 5 | 1 | 0 | 0%
13 | Wed May 6 | 2 | 0 | 0%

## Rubric Checklist
Rubric Coverage Checklist
Confirm ALL of these exist before submission. Check off as each is verified.
Category | Requirement | Verified By | Status
Minimum | 3+ data sources loaded into HDFS (you have 5) | Juan
Minimum | 2+ Spark joins across different sources (you have 3) | Yusuke
Minimum | 1+ Kafka topic with producer + Structured Streaming consumer | Quang
Minimum | 1+ windowed aggregation in streaming | Quang
Minimum | 1+ Airflow DAG with 4+ tasks and dependencies | Alex
Minimum | 1+ data quality gate in Airflow | Alex
Minimum | Working docker-compose.yml (docker compose up -d) | Juan
Minimum | Pipeline is idempotent (run twice, same result) | Alex
Stage 1 (8 pts) | Proper HDFS zone design (landing/curated/analytics) | Juan
Stage 1 (8 pts) | File format choices justified per dataset | Juan
Stage 1 (8 pts) | Replication strategy documented (one paragraph) | Juan
Stage 1 (8 pts) | Data loaded correctly into all zones | Juan
Stage 2 (10 pts) | Data cleaning applied (nulls, types, dedup) | Yusuke
Stage 2 (10 pts) | 2+ joins across different data sources | Yusuke
Stage 2 (10 pts) | Meaningful aggregations answering business questions | Yusuke
Stage 2 (10 pts) | Parquet output with appropriate partitioning | Yusuke
Stage 3 (10 pts) | Kafka topic design with rationale documented | Quang
Stage 3 (10 pts) | Working producer simulating real-time events | Quang
Stage 3 (10 pts) | Structured Streaming consumer | Quang
Stage 3 (10 pts) | Windowed aggregations or alerts | Quang
Stage 3 (10 pts) | Lambda/Kappa decision justified | Quang
Stage 4 (8 pts) | Scheduled DAG with 4+ tasks | Alex
Stage 4 (8 pts) | Quality gate between pipeline stages | Alex
Stage 4 (8 pts) | Retry logic configured | Alex
Stage 4 (8 pts) | Idempotent pipeline verified | Alex
Stage 4 (8 pts) | Monitoring/health-check DAG for streaming | Alex
Code & Docker (4 pts) | Clean, readable code with meaningful comments | TEAM
Code & Docker (4 pts) | Working docker-compose.yml (reproducible) | Juan
Code & Docker (4 pts) | Lightweight mode documented (Docker profiles) | Juan
Report (20 pts) | Executive Summary (1 page) | Helen
Report (20 pts) | Architecture Design (2 pages) with diagram | Helen
Report (20 pts) | Implementation (2-3 pages) including quality strategy | Helen
Report (20 pts) | Business Insights (1-2 pages) with specific numbers | Helen
Report (20 pts) | Scalability Discussion (1 page) with specific numbers | Helen
Report (20 pts) | Total length 6-10 pages as PDF | Helen
Presentation (25 pts) | Slide deck PDF committed to repo | Helen
Presentation (25 pts) | 10-12 min timing verified in rehearsal | Helen
Presentation (25 pts) | All team members speak substantively | TEAM
Presentation (25 pts) | Business-problem-first framing | Helen
Presentation (25 pts) | Demo screenshots/videos ready (no live Docker) | Helen
GitHub (5 pts) | Meaningful commit history (daily, not bulk upload) | TEAM
GitHub (5 pts) | Multiple team members contributing (visible) | TEAM
GitHub (5 pts) | Clear README with setup instructions | Juan
GitHub (5 pts) | Organized directory structure | Helen
GitHub (5 pts) | prof-tcsmith has repo access | Helen
README | Team member names listed | Helen
README | Project scenario summary | Helen
README | Architecture overview with diagram reference | Helen
README | Step-by-step setup instructions | Juan
README | Description of data sources with download link | Helen
README | Summary of key findings | Helen
Creativity (10 pts) | Above-minimum technical work done | TEAM
Creativity (10 pts) | Insightful business analysis with specific numbers | Helen
Creativity (10 pts) | Scalability with specific numbers (not vague) | Helen
Creativity (10 pts) | Tech decisions connected to business value | Helen
Rubric items verified: | 0 of 55
Completion %: | 0%