# MediaWave Streaming — Final Project Plan

Team of 5 · Target technical completion: May 1 · Submission: May 6

## Ground rules

- Every Quangommits to GitHub every day (empty commits OK for thinking days)

## Roles

- Juan — Integration Lead + Stage 1 (HDFS). Has 16 GB machine.

- Yusuke — Stage 2 (Spark batch)

- Quang — Stage 3 (Kafka + Streaming)

- Alex — Stage 4 (Airflow + Data Quality)

- Helen — PM + Writer + Project Management

## Day 1 — Friday, April 24

Juan — Docker inventory:

- Copy the 4 weekly docker-compose files into docker-research/

- In a scratch doc, list every service, every port mapping, every named volume, every network across all 4 files

- Identify all conflicts: port collisions, volume name clashes, network mismatches

- Deliverable: a conflict table shared at tomorrow's standup

Yusuke — Data understanding:

- Download all 5 MediaWave files + generate_data.py

- Set up Python venv: python -m venv venv && source venv/bin/activate && pip install pyspark==3.5.0 pandas jupyter

- Read generate_data.py end-to-end carefully

- Add a "Stage 2" section to docs/design.md with one entry per dataset: columns, types, nullable fields, expected value ranges, join keys

- Smoke test: load user-profiles.csv.gz with Spark, print schema, show 5 rows

Quang — Kafka reading + design:

- Re-read Week 10 Kafka materials

- pip install kafka-python

- Add a "Stage 3" section to docs/design.md: topic name, partition count, key design, retention, producer simulation strategy

- Write producers/event_producer.py skeleton that just prints fake JSON events to stdout

Alex — Airflow reading + quality helpers:

- Re-read Week 11 Airflow materials

- Add a "Stage 4" section to docs/design.md: DAG sketch with task list, dependencies, quality gate locations

- Create src/common/quality.py with three functions: check_row_count(df, min_rows), check_nulls(df, required_cols), check_unique_key(df, key_cols)

- Validate them in a notebook cell (no formal tests)

Helen — Repo + Canvas claim:

- Post on Canvas claiming Project #10 (do this first)

- Create GitHub repo, add prof-tcsmith as collaborator

- Build folder structure with .gitkeep files

- Write README skeleton with all section headers

- Initial commit + push, invite teammates

Day 1 green status:

- Project #10 claimed

- Repo live with 5 commits (one per person)

- A has conflict table, B has schema notes, C has topic design, D has quality functions, E has repo

## Day 2 — Saturday, April 25

Key: no cross-Alexependencies today. Everyone works independently.

Juan — First merge:

- Start docker-compose.yml using Week 11's file as the base

- Add HDFS services (namenode, datanode) from Week 8 on shared network mediawave-net, with mem_limit

- Add Spark services (spark-master, spark-worker) from Week 9

- Boot partial stack, verify HDFS UI at :9870 and Spark UI at :8080

- Smoke test: docker exec -it namenode hdfs dfs -mkdir /test && hdfs dfs -ls /

- Commit working file or commit WIP with clear prefix

Yusuke — Local cleaning prototypes:

- Create src/common/schemas.py with explicit StructType for all 5 datasets

- notebooks/02-spark-transforms.ipynb: load each dataset with explicit schema, run .count(), .describe(), null counts

- Draft reusable cleaning function:

- def clean_and_save(spark, input_path, output_path, schema, dedup_keys, required_cols):    df = spark.read.schema(schema).csv(input_path, header=True)    df = df.dropDuplicates(dedup_keys).dropna(subset=required_cols)    df.write.mode("overwrite").parquet(output_path)

- Apply to 2 simplest datasets (user-profiles, streaming-quality). Output to local ./curated/. Verify Parquet readable.

Quang — Producer to Kafka:

- Wait for A's Kafka (midday check). If not ready, run standalone Kafka in Docker temporarily.

- Expand producers/event_producer.py: read viewing-history.csv.gz, sort by timestamp, replay with small sleep, publish JSON to user-viewing-events

- Verify: docker exec -it kafka kafka-console-consumer --bootstrap-server kafka:9092 --topic user-viewing-events --from-beginning

- Deliverable: producer pushing ~50 events/sec visible in console

Alex — Skeleton DAG:

- Install Airflow locally or run lightweight Docker container

- dags/batch_pipeline.py with 5 placeholder BashOperator tasks: ingest, validate, clean, join, aggregate

- Config: schedule_interval="@daily", catchup=False, retries=2, retry_delay=timedelta(minutes=5)

- Verify Airflow UI shows DAG. One successful manual trigger run.

Helen — Architecture diagram v1:

- Diagram showing: 5 sources → HDFS landing → Spark batch → HDFS curated/analytics + Kafka → Structured Streaming → real-time output; Airflow orchestrating

- Export as docs/architecture-diagram.png

- Draft report/final-report.md sections 1 (Executive Summary) and 2 (Architecture Design)

Day 2 green status:

- A: HDFS + Spark booting together

- B: schemas file + 2 cleaned datasets to local Parquet

- C: producer writing to Kafka (or ready to)

- D: Airflow showing skeleton DAG

- E: Architecture diagram, draft report sections 1-2

## Day 3 — Sunday, April 26 — First integration checkpoint

Key dependency: A must finish full docker-compose stack by noon so C and D can integrate.

Juan — Full stack:

- Add Kafka (zookeeper + kafka) from Week 10

- Add Airflow (postgres + airflow) from Week 11

- Add profiles: ["full"] tags on Kafka + Airflow for lightweight mode

- Create HDFS zones and load raw files:

- docker exec namenode hdfs dfs -mkdir -p /landing/{user-profiles,viewing-history,content-catalog,user-interactions,streaming-quality} /curated /analyticsdocker cp data/user-profiles.csv.gz namenode:/tmp/docker exec namenode hdfs dfs -put /tmp/user-profiles.csv.gz /landing/user-profiles/

(repeat for all 5)

- Verify: hdfs dfs -ls -R /landing/ shows all 5 files

- Noon handoff call with B (15 min): walk through reading from HDFS inside Spark container

- Afternoon: draft README setup instructions

Yusuke — Switch to HDFS, clean remaining 3:

- Move notebook into Spark container environment

- Update src/common/config.py: LANDING = "hdfs://namenode:9000/landing", etc.

- Run yesterday's code against HDFS paths (should work unchanged)

- Clean the remaining 3: viewing-history, content-catalog (JSON), user-interactions (JSON)

- Verify all 5 curated Parquet files readable

- Commit cleaning code to src/transforms/

Quang — Streaming consumer:

- src/streaming/consumer.py: Spark Structured Streaming reading user-viewing-events, parsing JSON, writing to console

- Verify end-to-end flow

- Add windowed aggregation: count of play events per 1-minute tumbling window per content_id

- Commit producer and consumer

Alex — Connect DAG to real Spark:

- Replace BashOperator placeholders with SparkSubmitOperator or BashOperator calling spark-submit inside Spark container

- Wire ingest task to A's HDFS load

- Wire validate task to call quality.check_row_count on landing data

- Wire clean task to call B's cleaning script

- Trigger DAG manually. First 3 tasks should run. Allow 1-2 hours for Airflow → Spark networking debugging.

Helen — Report progress:

- Update architecture diagram to match what A actually built

- Expand Executive Summary with MediaWave business framing

- Start collecting screenshots: HDFS UI with files, Spark UI with workers, Airflow UI with DAG

Day 3 green status:

- Full stack boots with docker compose --profile full up -d

- All 5 MediaWave files in /landing/

- B has all 5 datasets cleaned to /curated/ as Parquet

- C has producer + streaming consumer + windowed aggregation working

- D has DAG running first 3 tasks for real

## Day 4 — Monday, April 27 — Joins + streaming depth

Juan — Integration testing + on-call:

- Stress test: docker compose down -v && docker compose --profile full up -d. Confirm cold-boot works.

- Document boot time in README

- Write "Lightweight mode" section of README with explicit commands

- On-call for B, C, D debugging

Yusuke — Joins + first aggregations:

- src/transforms/join_enrich.py:

  - Join 1: viewing-history ⨝ content-catalog on content_id

  - Join 2: viewing-history ⨝ user-profiles on user_id

  - Join 3: viewing-history ⨝ streaming-quality on session key

- src/transforms/aggregate_business.py:

  - Aggregation 1: top content by genre per week (/analytics/top_content_by_genre/, partitioned by week)

  - Aggregation 2: completion rate by subscription tier (/analytics/completion_by_tier/)

- Test from CLI: spark-submit aggregate_business.py

- Commit with docstrings explaining each business question answered

Quang — Lambda/Kappa writeup + richer streaming:

- Write Lambda vs. Kappa justification in docs/design.md Stage 3 section (Lambda fits MediaWave: historical=batch, live=stream)

- Enrich the single streaming consumer: compute multiple aggregations in the same job (top content + unique viewers + avg completion rate in the same window) and/or add a sliding window alongside the tumbling one

- One topic, one richer consumer — above minimum without topic sprawl

Alex — Real quality gate + remaining tasks:

- Implement real quality gate between clean and join: reads curated Parquet, runs check_nulls + check_row_count, raises AirflowFailException on failure

- Wire join to B's join_enrich.py

- Wire aggregate to B's aggregate_business.py

- Run full DAG end-to-end. Fix failures.

- Screenshot green DAG run

Helen — Implementation section + first slides:

- Draft Section 3 (Implementation): Kafka topic design, Airflow DAG structure, data quality strategy

- Take high-quality screenshots: docker stack boot, batch DAG running, streaming consumer showing live aggregations. Store in presentation/screenshots/.

- Create presentation/slides.pptx with title, agenda, team, problem statement, architecture slides (first 5)

Day 4 green status:

- B: 3 joins + 2 aggregations in /analytics/

- C: enriched streaming consumer + Lambda/Kappa writeup

- D: DAG runs end-to-end with real quality gate

- E: screenshots captured, slides 1-5 drafted

## Day 5 — Tuesday, April 28 — Finish Stage 2 + harden Stage 4

Juan:

- Pin all image versions in docker-compose (no latest)

- Write detailed README setup instructions, tested on a fresh clone

- Final docs/architecture-diagram.png polish

Yusuke — Finish aggregations:

- Aggregation 3: quality impact on completion (/analytics/quality_impact/)

- Aggregation 4: DAU by week + cohort retention (/analytics/dau_retention/, partitioned by week)

- notebooks/04-exploration.ipynb: load each analytics Parquet, produce one matplotlib plot per business question (4-5 plots total). Hand to E.

- Write src/transforms/README.md listing each analytics table, schema, business question answered

Quang — Streaming polish:

- Add checkpointing to streaming consumer (required for fault tolerance)

- Test: kill consumer mid-run, restart, verify resume without duplication

- Write src/streaming/README.md: topics, partitioning rationale, windowing choices

Alex — Idempotency + retries + SLA + monitoring DAG:

- Test idempotency: run batch DAG twice, confirm /curated/ and /analytics/ identical (use .mode("overwrite") in B's scripts)

- Add sla=timedelta(hours=2) to critical tasks

- Configure retries: 2 retries with exponential backoff on transform tasks

- Set email_on_failure=True, email="team-email@..." in default_args (satisfies failure alerting)

- Write dags/streaming_monitor.py: runs every 15 minutes, checks Kafka topic lag and streaming consumer health

- Screenshot successful runs for E

Helen:

- Draft Section 4 (Business Insights) using B's plots and analytics outputs. One paragraph per business question with a specific numeric finding.

- Slides 6-15: architecture, stage-by-stage walkthrough with screenshots

- Start Section 5 (Scalability). Talk to A, C, D for specific numbers on bottlenecks and cloud-service mappings.

Day 5 green status:

- All 4 aggregations done, documented

- Streaming with checkpointing

- Idempotency tested, SLA set, monitoring DAG live

- Report sections 1-4 drafted, slides 1-15 drafted

## Day 6 — Wednesday, April 29 — Full integration rehearsal

Goal: a grader could clone the repo and run everything. Test it.

Juan — Fresh-machine test:

- docker compose down -v, then follow your own README from scratch as if you were the grader

- Time each step, fix anything unclear

- Ask Helen to also clone and run setup — any issue E hits = README bug

Yusuke — Polish + documentation:

- Add partitioning to remaining large aggregations (.write.partitionBy("week").parquet(...))

- Clear docstrings on every Spark script

- Short screen capture (2-3 min): run a Spark job, show Parquet output, query with Spark SQL showing a business finding. Save to presentation/screenshots/.

Quang — End-to-end streaming demo:

- Short screen capture (2-3 min): start producer, show events in console, show Structured Streaming consumer output with windowed aggregates updating

- Save to presentation/screenshots/streaming-demo.mp4

- Final Lambda/Kappa writeup polished

Alex — DAG demo:

- Short screen capture (2-3 min): Airflow UI, trigger batch DAG, show tasks going green, show quality gate failing on injected bad data, show retry behavior

- Save to presentation/screenshots/dag-demo.mp4

Helen — Report + slides near-final:

- Full pass through report sections 1-5. Target 7-8 pages.

- Finalize all slides (20-25 slides for 10-12 min = ~30 sec/slide)

- Assign presentation sections: each person presents their own stage (~2 min each = 10 min, plus problem intro + closing)

Day 6 green status:

- Repo clones and runs on fresh machine

- Three 2-3 min demo videos recorded

- Report + slides 80% complete

## Day 7 — Thursday, April 30 — Polish + buffer

Buffer day. Use it for whatever is behind.

Everyone: code review, report review, slide review. Honest feedback.

If on track:

- A: final docker compose up -d test. Tag v0.9-rc.

- B: redo any weak aggregation. Improve visualizations.

- C: polish streaming docs.

- D: polish DAG documentation.

- E: full dry-run of presentation live on video call. Time it. Cut to ≤12 min.

- E: prepare 3-4 anticipated Q&A answers (half a page of notes) covering: schema evolution in streaming, Parquet vs. Avro choice, failure handling at 3 AM, late-arriving events.

If behind on anything: catch up today. No new features, only finishing.

## Day 8 — Friday, May 1 — Technical freeze

Goal: code freeze by EOD. No technical changes after today except critical bug fixes.

Morning (2-hour team call):

- Everyone watches A run docker compose up

- Everyone watches D trigger the batch DAG

- Everyone watches C run streaming demo

- Find bugs, fix immediately

Afternoon:

- A: final docker-compose polish. Tag v1.0-submission-candidate. Add "Known issues" to README if anything is imperfect.

- B: final Spark script polish. All scripts commented, all outputs documented.

- C: final streaming docs. Kafka topic justification finalized.

- D: final DAG polish. airflow dags test passes. Monitoring DAG confirmed running.

- E: report final pass. Slides final pass. Second full dry-run with team.

End of Day 8: technically done.

## May 2 — May 6: polish window

- May 2 (Sat): Each person reviews full report, gives red-pen feedback to E.

- May 3 (Sun): E incorporates feedback. Third full presentation rehearsal.

- May 4 (Mon): Final report PDF exported. Final slides PDF exported. Commit both.

- May 5 (Tue): Final dry-run, ideally on actual presentation room equipment.

- May 6 (Wed): Final commit, confirm prof-tcsmith access, submit. In-class presentation per Week 12 schedule.

## Rubric coverage checklist

Confirm all of these exist before submission:

Minimum technical requirements:

- [ ] 3+ data sources loaded into HDFS (you have 5)

- [ ] 2+ Spark joins across different sources (you have 3)

- [ ] 1+ Kafka topic with producer + Structured Streaming consumer

- [ ] 1+ windowed aggregation in streaming

- [ ] 1+ Airflow DAG with 4+ tasks and dependencies

- [ ] 1+ data quality gate in Airflow

- [ ] Working docker-compose.yml with docker compose up -d

- [ ] Pipeline is idempotent

Graded components:

- [ ] HDFS data lake: zone design, file format justification, replication strategy, data loaded

- [ ] Spark: cleaning, 2+ joins, aggregations answering business questions, Parquet with partitioning

- [ ] Streaming: Kafka topic design with rationale, producer, Structured Streaming consumer, windowed aggregation, Lambda/Kappa justified

- [ ] Airflow: 4+ tasks, quality gate, retry logic, idempotent, monitoring DAG

- [ ] Docker: working, reproducible, lightweight mode documented

- [ ] README with team, scenario, architecture, setup instructions, data sources, key findings

- [ ] 6-10 page report with all 5 required sections

- [ ] Slide deck PDF in repo

- [ ] Meaningful commit history, multiple contributors

- [ ] prof-tcsmith has repo access